## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Resource Allocation | Milestones | Dependencies | Progress (%) | Notes
P-001 | Define Productivity Goals | Jane Smith | 2024-03-01 | 2024-03-15 | Completed | High | Project Manager, HR Team | Goal Set Approval |  | 100% | Final goals approved by leadership.
P-002 | Conduct Employee Productivity Audit | John Doe | 2024-03-16 | 2024-04-10 | In Progress | Medium | Operations Team, Analytics Unit | Audit Report Drafting | P-001 | 65% | Data collection underway; analysis pending.
P-003 | Implement Time Tracking Tools | Lisa Chen | 2024-04-11 | 2024-05-30 | Planned | High | IT Department, HR Support | Tool Deployment & Training | P-002 | 0% | Final vendor selection pending.
P-004 | Develop Daily Stand-up Workflow | Mark Williams | 2024-05-01 | 2024-06-30 | Not Started | Medium | Team Leads, Operations | First Stand-up Session Plan |  | 0% | Drafting agenda and roles.
P-005 | Evaluate Productivity Metrics | Sarah Kim | 2024-06-01 | 2024-07-31 | Planned | High | Analytics Team, Finance | KPI Dashboard Launch | P-003 | 0% | Metric collection and visualization in progress.