## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Notes
Define Productivity Goals | John Smith | 2024-03-01 | 2024-03-15 | In Progress | High | Align team objectives with company KPIs.
Conduct Employee Productivity Audit | Sarah Johnson | <2024-03-16 | 2024-04-05 | Planned | Medium | Gather data on current workflow efficiency.
Implement Time-Tracking Tools | Michael Lee | 2024-04-06 | 2024-05-10 | Not Started | High | Select and deploy software for daily time logging.
Train Staff on Productivity Techniques | Lisa Wong | 2024-05-11 | 2024-06-01 | Planned | Medium | Host workshops on focus, task batching, and breaks.
Review Monthly Productivity Metrics | Team Lead | 2024-06-02 | 2024-06-30 | Not Started | Low | Assess improvements and adjust strategies.