## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Progress (%) | Resources Required
Define Productivity Goals | Jane Doe | 2024-03-01 | 2024-03-15 | In Progress | High | 60% | Project Manager, HR Team
Conduct Employee Productivity Audit | John Smith | 2024-03-16 | 2024-04-05 | Not Started | High | 0% | Data Analyst, IT Support
Implement Time-Tracking Tools | Alice Johnson | 2024-04-06 | 2024-05-10 | Planned | Medium | 20% | IT Team, Finance Department
Train Employees on New Tools | Robert Lee | 2024-05-11 | 2024-06-30 | Not Started | Medium | 0% | Training Coordinator, HR Team
Monitor and Evaluate Results | Jane Doe | 2024-07-01 | 2024-08-31 | Not Started | High | 0% | Operations Team, Analytics Team