## Worksheet
Project Phase | Objective | Key Activities | Resource Allocation | Timeline (Months) | Budget (USD) | KPIs | Risk Assessment
Initiation | Define scope, objectives, and feasibility of productivity improvement initiatives. | Stakeholder interviews, market analysis, SWOT assessment. | Project Manager (1), Business Analyst (1), IT Consultant (0.5) | 1 | $25,000 | Clear project scope definition, stakeholder buy-in. | Unclear market demand; low executive support.
Planning | Develop detailed roadmap, workflows, and resource plan for productivity enhancement. | Workload analysis, process mapping, tool selection (e.g., project management software). | Project Manager (1.5), Operations Lead (1), HR Coordinator (0.5) | 2 | $60,000 | On-time task planning, 20% efficiency gain target. | Tool integration delays; staff resistance to change.
Execution | Implement productivity tools, training, and revised workflows across departments. | Tool rollout, staff training sessions, pilot program launch. | Project Manager (2), Trainers (2), Department Heads (1) | 4 | $150,000 | 85% adoption rate, 15% increase in output. | Training dropouts; technical issues with software.
Monitoring & Optimization | Track performance, gather feedback, and refine processes based on data. | Weekly performance reviews, KPI dashboards, optimization workshops. | Project Manager (1), Data Analyst (1), Operations Team (full-time) | 3 | $40,000 | Monthly KPI improvement, 2% monthly efficiency gain. | Data access limitations; inconsistent reporting.
Closure | Formalize deliverables, document lessons learned, and transition to operations. | Final review meeting, report submission, handover documentation. | Project Manager (0.5), Documentation Lead (1) | 1 | $10,000 | All deliverables approved; stakeholder satisfaction ≥90%. | Delayed feedback cycle; incomplete documentation.
Total Project Budget |  |  |  | 10 | $285,000 | Overall productivity improvement target achieved.