## Worksheet
Productivity Improvement Project Template - Freelancer Style
Task / Activity | Owner | Priority Level | Deadline | Status | Resources Needed | Notes & Justification th>
Conduct Productivity Audit of Current Workflows | Sarah Johnson | Highest | 2024-04-15 | In Progress | Time tracking tool, workflow documentation | Identify bottlenecks and inefficiencies in daily tasks.
Set Up Time Blocking for Daily Scheduling | Marcus Lee | High | 2024-04-20 | Pending | Digital calendar, focus timers | Improve task prioritization and reduce distractions.
Implement Task Management System (e.g. Trello) | Amy Chen | High | 2024-05-01 | To Do | Access to cloud platform, team account setup | Enable real-time updates and team collaboration.
Weekly Performance Review Meetings | All Team Members (Rotating Facilitator) | Moderate | Every Friday, 10:00 AM | Not Started | Meeting agenda template, feedback forms | Track progress and adjust goals weekly.
Create Personal Productivity Goals for Q2 | Freelancer Self-Assign | Moderate | 2024-05-15 | To Do | Goal-setting worksheet, SMART criteria guide
Notes: