## Worksheet
Project Phase | Objective | Key Activities | Responsible Team | Timeline (MM/YY) | KPIs & Metrics | Risks & Mitigation
Initiation | Define project scope, goals, and alignment with productivity objectives. | Stakeholder interviews, requirement gathering, scope validation. | Project Office & Business Analysts | 03/2024 | Scope clarity; Alignment with strategic goals (≥90% stakeholder agreement). | Risk: Scope creep — Mitigation: Formal change control process.
Planning | Develop detailed project plan, resource allocation, and workflows. | Work breakdown structure (WBS), schedule development, budgeting. | Project Manager & Operations Team | 04/2024 | On-time delivery rate (>95%); Resource utilization (<30% idle time). | Risk: Budget overruns — Mitigation: Bi-weekly financial reviews.
Execution | Implement productivity tools, training, and operational changes. | Tool rollout, staff training sessions, process optimization pilots. | Operations & IT Departments | 05–08/2024 | Training completion rate (100%); System adoption (≥85% user usage). | Risk: Low user engagement — Mitigation: Gamified training modules and feedback loops.
Monitoring & Evaluation | Track progress, performance, and impact on productivity metrics. | Weekly reporting, data analysis, performance dashboards. | Analytics Team & PMO | 09–12/2024 | Daily output increase (%); Error rate reduction (>30% decrease). | Risk: Data inaccuracies — Mitigation: Automated data validation and audits.
Closure | Formally close the project and document lessons learned. | Final review, stakeholder sign-off, documentation archive. | Project Manager & Knowledge Manager | 01/2025 | Satisfaction score (≥4.5/5); Lessons learned repository completeness (100%). | Risk: Unresolved issues — Mitigation: Issue backlog review and post-mortem session.