## Worksheet
Task | Owner | Start Date | Due Date | Status | Progress (%) | Priority | Notes
Define Productivity Goals | John Smith | 2024-04-01 | 2024-04-15 | In Progress | 60% | High | Align with team objectives and KPIs.
Conduct Time Audit | Sarah Lee | 2024-04-05 | 2024-04-20 | Not Started | 0% | High | Log all work activities for a 30-day period.
Implement Task Management Tools | Mike Chen | 2024-04-10 | 2024-05-10 | Not Started | 0% | Medium | Set up Asana for project tracking.
Train Team on Productivity Techniques | Lisa Wong | 2024-05-01 | 2024-05-31 | Not Started | 0% | Medium | Host bi-weekly sessions on time blocking and focus techniques.
Review & Optimize Workflow | Project Manager | 2024-06-01 | 2024-06-30 | Not Started | 0% | High | Analyze data from audits and tools to refine processes.