## Worksheet
Weekly Productivity Improvement Project Template
Week Number | Date Range | Project Goal | Key Activities | Resources Needed | Status (✓ / ⚠️ / ✗) | Progress % th> | Risks & Challenges th> | Action Items (Next Week) th>
1 | Mon, Apr 8 – Sun, Apr 14 | Optimize daily workflow using task automation tools | Review current tasks; identify repetitive actions; implement automation scripts | Task management software (e.g., Asana), time tracking tool | ✓ | 75% | No major risks identified. Minor learning curve with new tools. | Complete script testing; train team on automation use.
2 | Mon, Apr 15 – Sun, Apr 21 | Improve meeting efficiency through structured agendas | Create standardized meeting templates; track agenda adherence | Meeting calendar sync, team feedback tool | ⚠️ | 50% | Some team members are resistant to new formats. | Host a workshop to demonstrate benefits; collect feedback.
3 | Mon, Apr 22 – Sun, Apr 28 | Reduce email volume by implementing response protocols | Categorize emails; set up auto-responders for common queries | Email filtering software, CRM integration | ✗ | 20% | Automation tools not properly configured; delays in implementation. | Fix configuration errors; assign point person to manage email flow.
4 | Mon, Apr 29 – Sun, May 5 | Improve time blocking for focused work sessions | Map daily schedule; block 90-minute deep work blocks | Digital calendar, focus timer app | ✓ | 85% | All team members successfully adopted time blocking. | Evaluate effectiveness via weekly productivity review.