## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Progress (%) | Priority
Project Initiation & Planning | Maria Santos | 2024-03-01 | 2024-03-15 | Completed | - | 100% | High
Market Research & Analysis | James Reed | 2024-03-16 | 2024-04-10 | In Progress | Project Initiation | 75% | Medium
Product Design & Prototyping | Lena Choi | 2024-04-11 | 2024-05-30 | Not Started | Market Research | 0% | High
Development Phase (Beta) | David Kim | 2024-06-01 | 2024-07-15 | Planned | Product Design | 0% | High
User Testing & Feedback Collection | Sophia Nguyen | 2024-07-16 | 2024-08-31 | Not Started | Development Phase | 0% | High
Final Product Launch | Team Lead - Alex Rivera | 2024-09-01 | 2024-09-30 | Not Started | User Testing | 0% | Critical