## Worksheet
Month | Project Phase | Key Activities | Responsible Team | Start Date | End Date | Progress %
January | Planning & Strategy | Define goals, scope, KPIs; stakeholder alignment | Product Management & Strategy Team | 01/01/2024 | 01/31/2024 | 100%
February | Resource Allocation | Assign roles, tools, budget planning; training setup | HR & Operations Team | 02/01/2024 | 02/28/2024 | 95%
March | Process Design & Workflow Setup | Design new workflows; implement productivity tools | Engineering & Operations Team | 03/01/2024 | 03/31/2024 | 85%
April | Pilot Implementation | Test new workflows in one department; collect feedback | Quality Assurance & Product Team | 04/01/2024 | 04/30/2024 | 75%
May | Full-Scale Rollout | Deploy across all departments; monitor performance | Productivity Council & IT Team | 05/01/2024 | 05/31/2024 | 65%
June | Performance Review & Optimization | Analyze KPIs; identify bottlenecks and refine processes | Analytics & Strategy Team | 06/01/2024 | 06/30/2024 | 80%
July | Team Training & Coaching | Conduct workshops; provide ongoing coaching sessions | HR & Leadership Development Team | 07/01/2024 | 07/31/2024 | 90%
August | System Integration & Automation | Automate repetitive tasks; integrate with existing platforms | IT & Engineering Team | 08/01/2024 | 08/31/2024 | 70%
September | Monitoring & Reporting | Establish dashboards; weekly review meetingsReporting & Operations Team | 09/01/2024 | 09/30/2024 | 85%
October | Stakeholder Feedback Loop | Collect feedback; adjust processes accordingly | Customer Success & Product Team | 10/01/2024 | 10/31/2024 | 95%
November | Continuous Improvement Plan | Finalize Q4 strategy; set 2025 goals | Productivity Council & Strategy Team | 11/01/2024 | 11/30/2024 | 98%
December | Annual Review & Celebration | Present results; celebrate achievements; plan next year | Executive Leadership & HR Team | 12/01/2024 | 12/31/2024 | 100%