## Worksheet
Task | Start Date | End Date | Responsible Person | Status
Define Productivity Goals | 2024-03-01 | 2024-03-15 | Jane Smith | Completed
Conduct Employee Survey | 2024-03-16 | 2024-03-31 | John Doe | In Progress
Analyze Current Workflows | 2024-04-01 | 2024-04-15 | Sarah Lee | Not Started
Propose Productivity Solutions | 2024-04-16 | 2024-05-05 | Mike Johnson | Not Started
Pilot Implementation (Phase 1) | 2024-05-06 | 2024-05-31 | Team A | Not Started
Evaluate Results & Adjust | 2024-06-01 | 2024-06-30 | Jane Smith | Not Started