## Worksheet
Task | Responsible Person | Start Date | End Date | Status | Progress (%)
Project Initiation & Planning | Project Manager | 2024-03-01 | 2024-03-15 | In Progress | 65%
Stakeholder Requirements Gathering | Business Analyst | 2024-03-16 | 2024-03-31 | Not Started | 0%
Process Workflow Design | UX Designer & Team Lead | 2024-04-01 | 2024-04-15 | Planned | 0%
Tool Selection & Integration | IT Operations Team | 2024-04-16 | 2024-05-10 | Not Started | 0%
Pilot Implementation (Phase 1) | Operations Manager | 2024-05-11 | 2024-06-05 | Planned | 0%
Performance Evaluation & Optimization | Productivity Analyst | 2024-06-06 | 2024-07-15 | Not Started | 0%
Full-Scale Rollout & Training | Executive Team | 2024-07-16 | 2024-08-31 | Not Started | 0%