## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Progress (%)
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | Project Manager | Completed | 100%
Requirement Gathering & Analysis | 2024-03-16 | 2024-04-10 | Business Analysts | In Progress | 75%
Design & Prototyping Phase | 2024-04-11 | 2024-05-05 | UX/UI Team | Not Started | 0%
Development & Coding | 2024-05-06 | 2024-07-15 | Software Developers | Not Started | 0%
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | QA Team | Not Started | 0%
Deployment & Go-Live | 2024-08-11 | 2024-08-31 | IT Operations | Not Started | 0%
Post-Launch Review & Feedback | 2024-09-01 | 2024-09-30 | Project Manager & Client | Not Started | 0%