## Worksheet
Task | Start Date | End Date | Responsible | Status
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | Maria Chen | Completed
Needs Assessment & Workshops | 2024-03-16 | 2024-04-05 | James Wilson | In Progress
Tool Selection & Vendor Evaluation | 2024-04-06 | 2024-04-25 | Lena Torres | Not Started
Pilot Implementation (Team A) | 2024-05-01 | 2024-05-31 | David Kim | Planned
Training & Change Management | 2024-06-01 | 2024-06-30 | Sarah Patel | Not Started
Full Organization Rollout | 2024-07-01 | 2024-08-31 | Project Office | Not Started
Performance Review & Optimization | 2024-09-01 | 2024-09-30 | Elena Gomez | Not Started