## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%)
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | John Smith | Completed | 100%
Requirement Gathering & Analysis | 2024-03-16 | 2024-04-10 | Sarah Lee | In Progress | 65%
Design & Wireframing | 2024-04-11 | 2024-05-05 | Michael Chen | Not Started | 0%
Development Phase (Frontend) | 2024-05-06 | 2024-06-15 | Emily Rodriguez | Not Started | 0%
Development Phase (Backend) | 2024-06-16 | 2024-07-30 | David Kim | Not Started | 0%
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | Lisa Wang | Not Started | 0%
Training & User Onboarding | 2024-09-01 | 2024-09-15 | James Taylor | Not Started | 0%
Launch & Post-Launch Review | 2024-09-16 | 2024-10-05 | Team Lead | Not Started | 0%