## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Priority
Define Productivity Goals | 2024-03-01 | 2024-03-15 | Jane Smith | Completed | High
Conduct Stakeholder Interviews | 2024-03-16 | 2024-03-31 | Mark Johnson | In Progress | Medium
Develop Workflow Optimization Plan | 2024-04-01 | 2024-04-30 | Sarah Lee | Planned | High
Implement Automation Tools | 2024-05-01 | 2024-05-31 | David Kim | Pending | Critical
Monitor Performance Metrics | 2024-06-01 | 2024-06-30 | Lisa Wong | Scheduled | Medium