## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Milestones | Resource Allocation | Risks & Mitigations | Progress (%)
Project Initiation & Planning | Jane Doe | 2024-03-01 | 2024-03-15 | 15 | Completed | - | Planning approved | Project Manager, Stakeholders | Scope creep risk - mitigation via stakeholder reviews | 100%
Market Research & Analysis | Mark Smith | 2024-03-16 | 2024-04-05 | 21 | In Progress | Project Initiation Completed | Data collection finalized | Research Team, Analytics Lead | Data access delays - mitigation via backup sources | 65%
Product Requirements Definition | Lisa Chen | 2024-04-06 | 2024-04-25 | 20 | Not Started | Market Research Completed | PRD Draft Review | Product Team, UX Lead | Stakeholder feedback loop - mitigation via scheduled workshops | 0%
UI/UX Design Phase | Alex Johnson | 2024-04-26 | 2024-05-15 | 21 | Not Started | PRD Approved | Wireframes approved | Design Team, UX Researcher | Design iteration delays - mitigation via parallel prototyping | 0%
Development & Coding | Team A (Dev) | 2024-05-16 | 2024-07-15 | 61 | Not Started | UI/UX Design Complete | Alpha build ready | Engineering Team, QA Lead | Technical debt - mitigation via refactoring sprints | 0%
Testing & Quality Assurance | Sarah Lee | 2024-07-16 | 2024-08-10 | 25 | Not Started | Development Complete | Bug report finalized | QA Team, Automation Lead | Critical bugs - mitigation via emergency sprint | 0%
User Training & Onboarding | Chris Wang | 2024-08-11 | 2024-08-30 | 20 | Not Started | Testing Completed | Training materials delivered | HR & Support Team | Low user engagement - mitigation via follow-up sessions | 0%
Go-Live & Deployment | Jane Doe (PM) | 2024-09-01 | 2024-09-05 | 5 | Not Started | Training Complete | Go-Live announced | IT Operations, DevOps Team | System downtime - mitigation via rollback plan | 0%
Post-Launch Review & Optimization | All Team | 2024-09-06 | 2024-10-15 | 31 | Not Started | Go-Live Successful | Feedback analysis complete | Product & Support Teams | Performance degradation - mitigation via monitoring upgrades | 0%