## Worksheet
Task | Responsible Person | Start Date | End Date | Status | Progress (%) | Notes/Comments
Project Initiation & Planning | John Smith | 2024-03-01 | 2024-03-15 | In Progress | 65% | Finalize project scope and objectives.
Resource Allocation & Team Setup | Lisa Chen | 2024-03-16 | 2024-03-25 | Not Started | 0% | Assign team members and tools.
Process Workflow Design | Michael Brown | 2024-03-26 | 2024-04-10 | Not Started | 0% | Map key workflows and identify bottlenecks.
Tool Implementation & Training | Sarah Lee | 2024-04-11 | 2024-05-05 | Not Started | 0% | Deploy new productivity tools and train staff.
Performance Monitoring & Review | David Kim | 2024-05-06 | 2024-05-31 | Not Started | 0% | Track KPIs, gather feedback, and adjust strategies.
Final Project Evaluation & Reporting | All Team Members | 2024-06-01 | 2024-06-15 | Not Started | 0% | Document lessons learned and create a final report.