## Worksheet
Task | Start Date | End Date | Responsible Employee | Status | Progress (%)
Define Productivity Goals | 2024-03-01 | 2024-03-15 | Jane Smith | Completed | 100%
Analyze Current Workflows | 2024-03-16 | 2024-04-05 | Mark Johnson | In Progress | 65%
Identify Time-Wasting Activities | 2024-04-06 | 2024-04-18 | Lisa Chen | Pending | 0%
Implement Time Management Tools | 2024-04-19 | 2024-05-31 | David Lee | Not Started | 0%
Evaluate Productivity Metrics Post-Implementation | 2024-06-01 | 2024-06-30 | Sarah Kim | Pending | 0%