## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Milestones | Resources Required | Risk Level
Project Kickoff Meeting | Project Manager | 2024-03-01 | 2024-03-01 | 1 | Completed | None | Kickoff Approved | Team, Meeting Room, Chair | Low
Requirements Gathering & Analysis | Business Analyst | 2024-03-02 | 2024-03-15 | 14 | In Progress | Kickoff Meeting | Requirements Finalized | Stakeholders, Documentation Tools | Medium
Product Design & Wireframing | UX Designer | 2024-03-16 | 2024-03-31 | 16 | Planned | Requirements Finalized | Design Approved | Design Tools, Feedback Sessions | Medium
Development Phase (Frontend) | Software Developer | 2024-04-01 | 2024-05-15 | 65 | Not Started | Design Approved | Alpha Version Ready | Development Team, Servers, Git | High
Development Phase (Backend) | Software Developer | 2024-04-01 | 2024-05-30 | 70 | Not Started | Design Approved | Beta Version Ready | Development Team, APIs, Databases | High
Testing & Quality Assurance | QA Engineer | 2024-06-01 | 2024-06-30 | 30 | Not Started | Alpha & Beta Versions Ready | Bug Report Summary Complete | Test Cases, Automation Tools | High
User Training & Onboarding | Training Manager | 2024-07-01 | 2024-07-15 | 15 | Planned | System Live & Tested | Training Materials Published | Trainers, Manuals, Video Content | Low
Go-Live & Deployment | Project Manager | 2024-07-16 | 2024-07-16 | 1 | Not Started | Training Completed | System Live | IT Team, Backup Systems, Monitoring Tools | High
Post-Go-Live Review & Feedback Collection | Project Manager | 2024-07-17 | 2024-08-15 | 29 | Not Started | Go-Live Complete | Feedback Report Submitted | Stakeholders, Survey Tools | Medium