## Worksheet
Task | Start Date | End Date | Responsible Party | Budget Allocation (USD) | Status | Progress (%)
Project Initiation & Feasibility Analysis | 2024-03-01 | 2024-03-15 | Project Manager | 15,000 | Completed | 100%
Stakeholder Requirements Gathering | 2024-03-16 | 2024-04-10 | Business Analysts | 20,000 | In Progress | 75%
Process Mapping & Workflow Optimization | 2024-04-11 | 2024-05-15 | Operations Team | 35,000 | Not Started | 0%
Technology Assessment & Tool Selection | 2024-05-16 | 2024-06-10 | IT Department | 40,000 | Planned | 0%
Pilot Implementation & Testing | 2024-06-11 | 2024-07-30 | Development Team | 75,000 | Not Started | 0%
Full-Scale Deployment & Training | 2024-08-01 | 2024-10-31 | All Departments | 150,000 | Not Started | 0%
Performance Evaluation & Reporting | 2024-11-01 | 2024-11-30 | Project Manager & Finance Team | 25,000 | Not Started | 0%
Total Budget Allocation: | [5 empty] | $360,000