## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Priority
Project Initiation & Planning | 01/04/2024 | 05/04/2024 | Freelancer A | In Progress | High
Market Research & Analysis | 06/04/2024 | 15/04/2024 | Freelancer B | Not Started | High
Product Design & Prototyping | 16/04/2024 | 30/04/2024 | Freelancer C | Planned | Medium
Development & Testing Phase | 01/05/2024 | 31/05/2024 | Freelancer D | Not Started | High
User Feedback & Iteration | 01/06/2024 | 15/06/2024 | Freelancer E | Not Started | Medium
Launch & Post-Launch Support | 16/06/2024 | 30/06/2024 | Freelancer A & B | Not Started | Low