## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%)
Define Productivity Goals | 2024-03-01 | 2024-03-15 | Sarah Johnson | Completed | 100%
Assess Current Work Habits | 2024-03-16 | 2024-03-31 | Michael Chen | In Progress | 65%
Create Daily Routine Plan | 2024-04-01 | 2024-04-15 | Emily Rodriguez | Not Started | 0%
Implement Time-Blocking Technique | 2024-04-16 | 2024-05-10 | James Wilson | Planned | 0%
Evaluate Weekly Productivity Metrics | 2024-05-11 | 2024-05-31 | Linda Park | Not Started | 0%
Adjust and Optimize Routine | 2024-06-01 | 2024-06-30 | Team Members | Not Started | 0%