## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Key Deliverables | Status | Progress (%)
Initiation & Planning | 01/15/2024 | 03/31/2024 | Strategy & Operations | Project charter, scope document, risk register | Completed | 100%
Product Design & Development | 04/01/2024 | 07/15/2024 | Product Innovation Team | UI/UX prototypes, feature specifications | On Track | 75%
Pilot Testing & Feedback | 07/16/2024 | 09/30/2024 | Engineering & QA | Beta release, user feedback report | In Progress | 40%
Full Deployment & Training | 10/01/2024 | 12/31/2024 | Sales & Support Team | User training modules, deployment checklist | Not Started | 0%
Post-Implementation Review | 01/01/2025 | 03/31/2025 | Project Management Office | Performance report, improvement plan | Planned | 0%