## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress %
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | Jane Doe (Project Manager) | Completed | 100%
Requirements Gathering | 2024-03-02 | 2024-03-15 | John Smith (Business Analyst) | In Progress | 65%
Design Phase Finalization | 2024-03-16 | 2024-03-31 | Lisa Chen (UI/UX Designer) | Planned | 0%
Development Sprint 1 | 2024-04-01 | 2024-04-15 | Mike Brown (Developer Team) | Not Started | 0%
QA Testing & Bug Fixes | 2024-04-16 | 2024-05-05 | Sarah Lee (QA Lead) | Not Started | 0%
Training & Onboarding | 2024-05-06 | 2024-05-15 | David Kim (Training Manager) | Not Started | 0%
Go-Live & Post-Implementation Review | 2024-05-16 | 2024-05-31 | Jane Doe (Project Manager) | Not Started | 0%