## Worksheet
Month | Project Phase | Key Activities | Responsible Team | Start Date | End Date th> | Status | Progress (%)
January | Planning & Scope Finalization | Define objectives, gather stakeholder input, finalize project scope | Project Management Team | 2024-01-01 | 2024-01-31 | Completed | 100%
February | Resource Allocation & Team Setup | Assign roles, budget planning, tool configuration | HR & Operations Team | 2024-02-01 | 2024-02-28 | In Progress | 75%
March | Process Design & Workflow Mapping | Develop new productivity workflows, create templates | Productivity Team | 2024-03-01 | 2024-03-31 | Not Started | 0%
April | Pilot Implementation | Run pilot in one department, collect feedback | Operations & IT Team | 2024-04-01 | 2024-04-30 | Planned | 0%
May | Full-Scale Rollout | Deploy across all departments, train staff | Project Management & Training Team | 2024-05-01 | 2024-05-31 | Not Started | 0%
June | Performance Review & Optimization | Analyze KPIs, refine processes based on data | Analytics & Strategy Team | 2024-06-01 | 2024-06-30 | Not Started | 0%