## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Key Deliverables | Status
Phase 1: Planning & Assessment | 01/01/2024 | 03/15/2024 | Productivity Steering Committee | Scope review, stakeholder interviews, baseline metrics | On Track
Phase 2: Process Mapping & Analysis | 03/16/2024 | 05/31/2024 | Operations & Operations Analytics Team | Workflow diagrams, bottlenecks report, efficiency scorecards | In Progress
Phase 3: Tool Implementation | 06/01/2024 | 08/31/2024 | IT & Digital Transformation Team | Productivity software rollout, user training modules | Planned
Phase 4: Pilot Testing & Feedback Loop | 09/01/2024 | 10/31/2024 | User Experience & HR Teams | Pilot results, user feedback survey, optimization plan | Scheduled
Phase 5: Full Deployment & Monitoring | 11/01/2024 | 12/31/2024 | All Departments & Central Ops | Org-wide rollout, KPI dashboards, monthly reviews | Not Started
Project Timeline – Productivity Improvement Initiative (Multi-Page Template)