## Worksheet
Task | Responsibility | Start Date | End Date | Status | Progress (%)
Define Productivity Goals | Project Manager | 2024-03-01 | 2024-03-15 | Completed | 100%
Conduct Team Productivity Audit | HR & Operations Lead | 2024-03-16 | 2024-03-31 | In Progress | 65%
Identify Productivity Tools & Software | IT Department | 2024-04-01 | 2024-04-15 | Not Started | 0%
Implement New Workflow Procedures | Operations Team | 2024-04-16 | 2024-05-31 | Not Started | 0%
Train Staff on New Tools | Training Coordinator | 2024-06-01 | 2024-06-30 | Not Started | 0%
Evaluate Productivity Metrics & Adjust | Project Manager | 2024-07-01 | 2024-07-31 | Not Started | 0%