## Worksheet
Task | Owner | Start Date | End Date | Status | Priority
Define Productivity Goals | Jane Doe | 2024-03-01 | 2024-03-10 | In Progress | High
Conduct Staff Productivity Audit | John Smith | 2024-03-11 | 2024-03-25 | Not Started | High
Implement Task Management Tools | Alex Chen | 2024-03-26 | 2024-04-15 | Planned | Medium
Train Employees on New Tools | Sarah Kim | 2024-04-16 | 2024-04-30 | Not Started | Medium
Measure & Analyze Productivity Metrics | David Lee | 2024-05-01 | 2024-05-31 | Planned | High
Review & Adjust Strategies | Team Lead | 2024-06-01 | 2024-06-15 | Not Started | High