## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Priority
Define Productivity Goals | Jane Doe | 2024-03-01 | 2024-03-05 | 5 | In Progress | High
Conduct Staff Productivity Audit | John Smith | <2024-03-06 | 2024-03-15 | 10 | Planned | Medium
Develop Time Management Training Modules | Lisa Chen | 2024-03-16 | 2024-04-10 | 25 | Not Started | High
Implement Workflow Automation Tools | Mike Taylor | 2024-04-11 | 2024-05-15 | 35 | Planned | High
Measure KPIs and Review Performance | Sarah Brown | 2024-05-16 | 2024-06-30 | 45 | Not Started | Medium