## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Priority
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | John Smith | Completed | High
Needs Assessment & Workflow Analysis | 2024-03-16 | 2024-04-05 | Sarah Lee | In Progress | High
Tool Selection & Configuration | 2024-04-06 | 2024-04-25 | Mike Chen | Planned | Medium
Employee Training & Onboarding | 2024-05-01 | 2024-05-15 | Lisa Wong | Scheduled | Medium
Pilot Implementation & Feedback Loop | 2024-05-16 | 2024-06-10 | David Park | Not Started | High
Full-Scale Deployment | 2024-06-11 | 2024-07-30 | Project Team | Planned | High
Post-Implementation Review & Optimization | 2024-08-01 | 2024-08-31 | Alex Turner | Not Started | Medium