## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%)
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | John Smith | Completed | 100%
Needs Assessment & Analysis | 2024-03-02 | 2024-03-15 | Lisa Chen | In Progress | 65%
Stakeholder Workshops | 2024-03-16 | 2024-03-25 | Mark Taylor | Not Started | 0%
Solution Design & Prototyping | 2024-03-26 | 2024-04-10 | Sarah Kim | Not Started | 0%
Development & Testing Phase | 2024-04-11 | 2024-05-15 | Team A (Dev) | Not Started | 0%
Training & Change Management | 2024-05-16 | 2024-06-05 | David Brown | Not Started | 0%
Go-Live & Post-Implementation Review | 2024-06-06 | 2024-06-15 | Project Manager | Not Started | 0%