## Worksheet
Task | Start Date | End Date | Responsible Person | Status
Define Productivity Goals | 2024-03-01 | 2024-03-05 | Alex Johnson | Completed
Conduct Employee Productivity Audit | 2024-03-06 | 2024-03-15 | Sarah Lee | In Progress
Develop New Workflow Templates | 2024-03-16 | 2024-04-10 | Mike Chen | Not Started
Train Employees on New Tools | 2024-04-11 | 2024-04-25 | Lisa Wong | Planned
Measure and Monitor Productivity Results | 2024-04-26 | 2024-05-31 | David Park | Not Started