## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%)
Define Productivity Goals | Alex Johnson | 2024-03-15 | 2024-03-20 | Completed | 100%
Conduct Employee Survey | Sarah Lee | 2024-03-21 | 2024-03-28 | In Progress | 65%
Implement Time Tracking Tool | Mike Chen | 2024-03-30 | 2024-04-15 | Not Started | 0%
Train Team on New Tools | Lisa Wong | 2024-04-16 | 2024-04-30 | Planned | 0%
Review Monthly Productivity Reports | Team Lead | 2024-05-01 | 2024-05-31 | Not Started | 0%