## Worksheet
Task | Owner | Start Date | End Date | Status | Priority
Market Research & Competitor Analysis | Alex Morgan | 2024-03-01 | 2024-03-15 | In Progress | High
Product Roadmap Finalization | Jordan Lee | 2024-03-16 | 2024-04-05 | On Track | High
Team Onboarding & Skill Alignment | Samira Patel | 2024-03-05 | 2024-03-31 | Completed | Medium
User Feedback Loop Setup | Taylor Kim | 2024-04-06 | 2024-05-10 | Planned | Medium
Automation Workflow Design | Miguel Ruiz | 2024-04-15 | 2024-05-30 | Pending | High
Weekly Productivity Review Meeting | All Team Leads | Every Friday, 10:00 AM | Ongoing | Ongoing | Medium