## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%)
Define Productivity Goals | 2024-03-01 | 2024-03-15 | John Smith | Completed | 100%
Conduct Process Audit | 2024-03-16 | 2024-04-05 | Sarah Lee | In Progress | 75%
Identify Time-Wasting Activities | 2024-04-06 | 2024-04-20 | Michael Brown | Pending | 0%
Implement Tool Integration (Task Management) | 2024-04-21 | 2024-05-10 | Lisa Chen | Planned | 0%
Train Team on New Workflows | 2024-05-11 | 2024-05-30 | All Team Members | Pending | 0%
Monitor and Adjust Performance Metrics | 2024-06-01 | 2024-06-30 | John Smith | Pending | 0%