## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Progress (%)
Define Productivity Goals | Team Lead | 2024-03-01 | 2024-03-15 | In Progress | None | 60%
Conduct Team Productivity Audit | Operations Manager | 2024-03-16 | 2024-03-31 | Not Started | Goal Definition | 0%
Identify Process Bottlenecks | Process Analyst | 2024-04-01 | 2024-04-15 | Not Started | Audit Completed | 0%
Implement Time Management Tools | IT Coordinator | 2024-04-16 | 2024-05-10 | Not Started | Bottlenecks Identified | 0%
Train Team on New Tools | Training Lead | 2024-05-11 | 2024-05-30 | Not Started | Tools Deployed | 0%
Evaluate and Refine Process | Team Lead | 2024-06-01 | 2024-06-30 | Not Started | Training Completed | 0%