## Worksheet
Task | Responsibility | Start Date | End Date | Status | Progress (%)
Define Project Scope & Objectives | Project Manager | 2024-03-01 | 2024-03-15 | Completed | 100%
Stakeholder Requirements Gathering | Business Analyst | 2024-03-16 | 2024-04-05 | In Progress | 75%
Develop Project Plan & Timeline | Project Manager | 2024-04-06 | 2024-04-18 | Not Started | 0%
Team Training & Tool Setup | IT Department | 2024-04-19 | 2024-05-03 | Not Started | 0%
Pilot Phase Implementation | Development Team | 2024-05-04 | 2024-06-15 | Not Started | 0%
Review & Optimization Cycle | Project Manager | 2024-06-16 | 2024-07-10 | Not Started | 0%
Full-Scale Deployment | Operations Team | 2024-07-11 | 2024-08-31 | Not Started | 0%