## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%) | Milestones Reached
Project Planning & Scope Definition | 2024-03-01 | 2024-03-15 | Sarah Johnson | Completed | 100% | Scope finalized, stakeholders aligned
Requirement Gathering & Analysis | 2024-03-16 | 2024-04-10 | Michael Chen | In Progress | 75% | Initial requirements documented
Design & Workflow Development | 2024-04-11 | 2024-05-05 | Lisa Rodriguez | Not Started | 0%
Development & Coding Phase | 2024-05-06 | 2024-07-15 | Team Alpha (Dev) | Not Started | 0%
Testing & Quality Assurance | 2024-07-16 | 2024-08-10 | David Kim | Not Started | 0%
Deployment & Go-Live | 2024-08-11 | 2024-08-31 | Operations Team | Not Started | 0%
Post-Implementation Review | 2024-09-01 | 2024-09-15 | Project Steering Committee | Not Started | 0%