## Worksheet
Week | Project Phase | Key Activities | Responsible Person | Deadline | Status
1 | Initiation & Planning | Define goals, scope, and team roles | Project Manager | 2024-04-08 | Completed
2 | Requirement Gathering | Stakeholder interviews, document needs | Business Analysts | 2024-04-15 | In Progress
3 | Design Development | Create wireframes and user flows | UX/UI Team | 2024-04-22 | Pending
4 | Development Phase | Build core functionality in sprints | Software Developers | 2024-04-29 | Planned
5 | Testing & Quality Assurance | Functional and performance testing | QA Engineers | 2024-05-06 | Not Started
6 | Deployment & Launch | Roll out to production, user training | IT Operations | 2024-05-13 | Not Started