## Worksheet
Project ID | Project Name | Team Member | Start Date | End Date | Current Status | Priority Level | Progress (%) | Milestones Achieved | Next Action Item | Responsible For | Notes
PRJ-001 | Streamline Daily Workflow | Alex Morgan | 2024-03-15 | 2024-05-30 | In Progress | High | 65% | Phase 1 complete, Phase 2 underway | Optimize task allocation in Trello | Alex Morgan | Enhanced team communication logs for better tracking.
PRJ-002 | Implement Time Tracking Tool | Jamie Lee | 2024-04-01 | 2024-06-15 | On Hold | Medium | 30% | Tool evaluation phase complete | Finalize vendor selection by April 20 | Jamie Lee | Waiting on budget approval from Finance.
PRJ-003 | Weekly Stand-up Optimization | Taylor Reed | 2024-03-25 | 2024-07-31 | Completed | Low | 100% | All milestones met with 2-day buffer | — | Taylor Reed | Positive feedback from cross-functional teams.
PRJ-004 | Automate Report Generation | Jordan Kim | 2024-05-01 | 2024-08-31 | Planned | High | 0% | — | Define report templates and data sources | Jordan Kim | Needs input from Finance and Analytics teams.