## Worksheet
Project ID | Project Name | Objective | Start Date | End Date | Current Status | Responsible Team | Progress (%) | Key Deliverables | Next Milestone
PRD-2024-001 | Streamline Daily Workflow | Reduce task completion time by 30% through automation tools. | 2024-03-15 | 2024-06-30 | On Track | Productivity & Operations Team | 75% | Automated task scheduler, daily report dashboard | Finalize automation rollout (June 15)
PRD-2024-002 | Enhance Meeting Efficiency | Cut meeting duration by 25% with agenda templates and time tracking. | 2024-04-01 | 2024-07-31 | Active | Team Leadership & HR | 50% | Agenda templates, meeting time logs, post-meeting summaries | Pilot launch in Department A (May 15)
PRD-2024-003 | Introduce Focus Time Blocks | Improve deep work by implementing time-blocking strategies. | 2024-05-10 | 2024-08-31 | Planning Phase | Employee Wellness & Productivity Committee | 25% | Focus block schedule, productivity journal, employee feedback form | First pilot with 10 team members (June 1)
PRD-2024-004 | Optimize Resource Allocation | Improve team utilization by analyzing workload distribution. | 2024-03-28 | 2024-10-31 | In Progress | Operations & Data Analytics Team | 65% | Workload heatmaps, resource optimization model, staffing plan | Final report and recommendations (September 10)