## Worksheet
Project Name | Objective | Start Date | End Date | Responsible Team | Progress (%) | Status | Key Milestones | Budget (USD) | Resources Required
Streamline Reporting Process | Automate weekly reports to reduce manual input by 50% | 2024-01-15 | 2024-12-31 | Operations & Analytics Team | 75% | On Track | Q1 Kickoff, Q2 Prototype, Q3 Testing, Q4 Launch | 15,000 | 2 analysts, 3 developers
Implement Time Tracking System | Improve task visibility and reduce idle time by 30% | 2024-03-01 | 2024-11-30 | HR & Project Management | 40% | In Progress | Q2 Design, Q3 Pilot, Q4 Full Deployment | 12,500 | 1 project manager, 4 IT staff
Optimize Meeting Schedule | Reduce meeting frequency by 25% and increase focus time | 2024-04-10 | 2024-12-31 | Leadership & Office Management | 60% | On Track | Q4 Review, Q1 Optimization, Q2 Implementation | 8,000 | 3 coordinators, 1 scheduler
Introduce Weekly Productivity Reviews | Increase team self-assessment and goal clarity | 2024-05-01 | 2024-12-31 | All Teams (Cross-functional) | 20% | Planning Phase | Q3 Pilot, Q4 Full Rollout | 5,000 | 1 facilitator per team