## Worksheet
Project Name | Owner | Start Date | End Date | Status | Progress (%) | Budget (USD) | Actual Spend (USD) | Next Milestone | Notes
Team Productivity Dashboard Launch | Sarah Johnson | 2024-03-15 | 2024-06-30 | In Progress | 65% | $15,000 | $12,300 | User Training Phase (May 15) | Initial rollout in Q2; feedback loop active.
Daily Stand-Up Optimization | Mark Lee | 2024-04-01 | 2024-07-31 | Planning | 15% | $8,000 | $2,100 | Pilot in Department A (May 3) | Measure efficiency gains via time tracking.
Automated Task Scheduling Tool | Lisa Chen | 2024-05-01 | 2024-11-30 | Not Started | 0% | $30,000 | $0 | Requirements Finalized (June 15) | Integration with existing CRM.
Weekly Performance Review System | David Kim | 2024-06-01 | 2024-10-31 | In Progress | 45% | $12,500 | $9,800 | Data Validation Phase (July 10) | Ensure compliance with HR policy.