## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%)
Conduct productivity audit of current workflows | Jane Smith | 2024-04-10 | In Progress | High | 60%
Implement time-tracking tool for team members | Mark Johnson | 2024-04-15 | Not Started | High | 0%
Develop daily stand-up protocol | Lisa Chen | 2024-04-20 | Planned | Medium | 0%
Train team on new task management system | Robert Davis | 2024-05-05 | Scheduled | Medium | 0%
Review and optimize meeting schedule | Sophia Brown | 2024-05-10 | Not Started | Low | 0%