## Worksheet
Date | Task | Priority | Estimated Time (min) | Actual Time (min) | Status | Notes
2023-10-05 | Review project timeline | High | 30 | 35 | Completed | Updated milestones based on team feedback.
2023-10-05 | Prepare daily stand-up presentation | Medium | 45 | 40 | Completed | Delivered to team in morning meeting.
2023-10-05 | Follow up with client on feature request | High | 60 | 55 | Completed | Client approved the scope adjustment.
2023-10-06 | Update task board with progress | Low | 20 | 25 | Completed | Added new tasks and updated due dates.
2023-10-06 | Conduct team productivity audit | High | 90 | 85 | Completed | Identified 3 time-wasting activities; action plan in progress.