## Worksheet
Project Name | Objective | Start Date | End Date | Responsible Person | Status | Progress (%) | Key Milestones | Budget (USD) | Resource Allocation | Risk Assessment | Dependencies | Improvement Actions
Team Workflow Optimization | Streamline daily team operations using digital tools and standardized processes. | 2024-03-01 | 2024-06-30 | Sarah Johnson | On Track | 85% | Project kickoff, tool adoption, process review | $15,000 | 3 full-time members, 2 part-time consultants | Low - Tool integration delays | IT system upgrades, HR onboarding process | Weekly standups, automate report generation
Remote Work Policy Enhancement | Improve remote productivity through updated policies and communication protocols. | 2024-04-15 | 2024-08-31 | Michael Chen | In Progress | 50% | Policy draft approval, employee feedback survey | $8,500 | HR team, IT support staff | Medium - Employee resistance to policy changes | Executive buy-in, training sessions | Implement flexible work hours and async communication tools
Time Tracking System Rollout | Introduce a centralized time tracking system to monitor employee efficiency. | 2024-05-01 | 2024-11-30 | Lisa Park | Planning Phase | 20% | Vendor selection, pilot group setup, user training plan | $25,000 | 1 project manager, 3 analysts | High - Data privacy concerns | Legal review, compliance audit, data encryption implementation | Establish baseline performance metrics for comparison