## Worksheet
Project Name | Team Member | Start Date | End Date | Status | Progress (%) | Key Deliverables | Milestones Achieved | Risks & Issues | Next Actions
Enhanced Workflow Automation | Sarah Chen, James Lee | 2024-03-01 | 2024-04-30 | On Track | 85% | Automated reporting pipeline, reduced manual entry by 60% | Completed Q1 testing; launched pilot in March | Minor integration delay with legacy system | Resolve integration issues by April 15
Team Productivity Training Program | Emily Rodriguez, David Kim | 2024-03-15 | 2024-05-31 | In Progress | 45% | Weekly productivity workshops, time management modules | Completed first 3 sessions; attendance rate at 80% | Low engagement in remote teams | Introduce interactive tools and peer accountability groups
Client Onboarding Process Optimization | Michael Brown, Lisa Wong | 2024-04-01 | 2024-06-30 | Planning Phase | 15% | Streamlined intake form, automated onboarding checklist | Initial requirements gathered; feedback from 5 clients collected | Need more client input on process flow | Conduct additional client interviews in April
Remote Work Environment Setup | Rachel Taylor, Thomas Garcia | 2024-03-01 | 2024-05-31 | On Track | 90% | Set up secure remote access, collaboration tools, and IT support protocol | All teams equipped; productivity surveys show positive response | Occasional connectivity issues in low-bandwidth areas | Improve bandwidth solutions for regional offices