## Worksheet
Project Name | Objective | Start Date | End Date | Responsible Team | Current Status | Progress (%) | Key Milestones | Dependencies | Risks & Issues
Streamline Workflow Automation | Reduce manual tasks by 40% through process automation tools. | 2024-03-15 | 2024-07-30 | Operations & IT Team | On Track | 65% | Design automation flow, Pilot with department A, Full rollout. | IT infrastructure update, Vendor API access | No critical risks identified.
Enhance Team Collaboration Tools | Implement unified platform to improve team communication and task tracking. | 2024-04-01 | 2024-09-15 | Project Management Office (PMO) | In Progress | 35% | Tool selection, Training schedule, User onboarding. | Training availability, Employee resistance | Training delays due to scheduling conflicts.
Optimize Daily Meeting Efficiency | Reduce meeting time by 30% through agenda standardization and pre-reads. | 2024-05-10 | 2024-11-30 | All Departments (Cross-functional) | Delayed | 15% | Adopt meeting templates, Weekly review of outcomes, Feedback loop. | Departmental workload peaks in Q3 | Pending buy-in from senior leaders.
Introduce Time-Tracking System | <Improve time utilization by identifying inefficiencies and enabling data-driven decisions. | 2024-06-01 | 2024-10-31 | HR & Finance Departments | On Track | 85% | System integration, Employee training, Data validation. | Integration with payroll system | Minor data entry errors during pilot phase.