## Worksheet
Project Name | Owner | Start Date | Target Completion Date | Current Status | Progress (%) | Key Deliverables | Next Action Item | Risk/Issue Log
Team Workflow Optimization | Sarah Johnson | 2024-03-15 | 2024-06-15 | On Track | 85% | Process documentation, time tracking tool integration | Finalize user training schedule
Daily Stand-up Implementation | Michael Chen | 2024-04-01 | 2024-05-31 | In Progress | 60% | Daily meeting template, participation tracking | Conduct pilot with 3 teams | Team resistance to meetings
Remote Collaboration Tools Upgrade | Lisa Park | 2024-03-20 | 2024-07-15 | Planned | 15% | Cloud-based project management, real-time updates | Begin vendor evaluation process | Budget constraints identified
Meeting Efficiency Audit | David Rodriguez | 2024-03-10 | 2024-05-30 | On Track | 95% | Meeting minutes standardization, agenda templates | Present findings to leadership team